## TL
ID | Task Name | Duration | Start | Finish | Assigned Roles
0 | Project Timeline | 70 Days | January 25th | May 5th
1 | CIS4339 Spring 2023 - Project | 70 Days | January 25th | May 5th
2 | Sprint 1 - Compose Functional Specification Document | 11 Days | January 25th | February 15th
3 | Review Initial Application Functions and Code | 13 Days | January 25th | February 6th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
4 | Determine End-User Needs | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
5 | Determine Changes Required to Current UI to Satisfy Requirements | 2 Days | February 6th | February 8th
6 | Login and User Authentication Function | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
7 | Dashboard Chart Function | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
8 | Event Services Function | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
9 | Develop Use Case Scenarios for New Features | 2 Days | February 6th | February 8th
10 | Use Case for Login Functionality | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
11 | Use Case for Event Services - CRUD | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
12 | Develop Flow Diagrams for New Features | 2 Days | February 6th | February 8th
13 | User Flow Diagrams for Login and Authentication Function | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
14 | User Flow Diagrams for Event Services Function - CRUD | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
15 | Develop Outline & Assign Roles | 2 Days | February 6th | February 8th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
16 | Review and Update Functional Specification Document | 8 Days | February 8th | February 15th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
17 | Submit Final Functional Specification Document | 1 Day | February 15th | February 15th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
18 | Sprint 1 Completion | 1 Day | February 15th | February 15th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
19 | Sprint 2 - Implemenation of New Features in Front-End UI | 21 Days | Febuary 16th | March 7th
20 | Dashboard | 3 Days | Febuary 16th | February 18th
21 | Update Dashboard Chart to have a Pie Chart Showing all Current Clients per Zipcode | 3 Days | Febuary 16th | February 18th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
22 | Login and User Authentication Implementation | 7 Days | February 19th | February 25th
23 | Add Login Link on Home Page | 7 Days | February 19th | February 25th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
24 | Hide Menu Options for Unauthenticated Users | 7 Days | February 19th | February 25th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
25 | Create a Login-In Form to Authenticate All Users | 7 Days | February 19th | February 25th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
26 | Create a Prompt If User and/or Password is Incorrect | 7 Days | February 19th | February 25th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
27 | Create a Prompt When a User is Not Registered | 7 Days | February 19th | February 25th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
28 | Create a Function to Unhide Menu when Users are Authenticated | 7 Days | February 19th | February 25th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
29 | Event Services Implementation | 7 Days | Febuary 26th | March 3rd
30 | Update UI Menu Options to Add | 7 Days | Febuary 26th | March 3rd | Klein, Trinity; Abejide, Maria; Macedo, Joanna
31 | Create a view to list and search all current events | 7 Days | Febuary 26th | March 3rd | Klein, Trinity; Abejide, Maria; Macedo, Joanna
32 | Implement UI to Add an Event Service | 7 Days | Febuary 26th | March 3rd | Klein, Trinity; Abejide, Maria; Macedo, Joanna
33 | Implement UI to Update an Event Information | 7 Days | Febuary 26th | March 3rd | Klein, Trinity; Abejide, Maria; Macedo, Joanna
34 | Implement UI to Delete an Event Information | 7 Days | Febuary 26th | March 3rd | Klein, Trinity; Abejide, Maria; Macedo, Joanna
35 | Implement UI to Open an Event Information | 7 Days | Febuary 26th | March 3rd | Klein, Trinity; Abejide, Maria; Macedo, Joanna
36 | Review UI and Functionality Changes | 3 Days | March 4th | March 6th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
37 | Approve Implemented UI and Functionality Changes | 1 Day | March 7th | March 7th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
38 | Sprint 2 Completion | 1 Day | March 7th | March 7th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
39 | Sprint 3 - Expansion of Backend API and Documentation and Presentation | 36 Days | March 8th | April 30th
40 | Implemention of API and Documents | 23 Days | March 8th | March 29th
41 | Implement API Service to Get Clients Ordered By Zipcode on Pie Chart in Dashboard | 8 Days | March 8th | March 15th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
42 | Implement API Service to Authenticate Users Through a Username, Password, and User Groups | 23 Days | March 8th | March 29th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
43 | Implement API Service to Update Event Service | 23 Days | March 8th | March 29th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
44 | Implement API Service to Delete Event Service | 23 Days | March 8th | March 29th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
45 | Implement API Service to Create Event Service | 23 Days | March 8th | March 29th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
46 | Implement API Service to Read Event Service | 23 Days | March 8th | March 29th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
47 | Test API Functions | 8 Days | March 30th | April 6th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
48 | Update API and Documents | 7 Days | April 6th | April 12th
49 | Update Dashboard API Documents | 7 Days | April 6th | April 12th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
50 | Update Login API Documents | 7 Days | April 6th | April 12th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
51 | Update Event Service API Documents | 7 Days | April 6th | April 12th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
52 | Review and Update API Implementations and Documents | 5 Days | April 13th | April 29th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
53 | Record and Edit Presentation Video of Project Features | 5 Days | April 19th | April 29th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
54 | Sprint 3 Completed | 1 Day | April 30th | April 30th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
55 | Sprint 4 - Individual Peer Evaluations | 5 Days | May 1st | May 5th
56 | Evaluate Two Peers Project | 5 Days | May 1st | May 5th | Klein, Trinity; Abejide, Maria; Macedo, Joanna
57 | Spring 4 Completed | 1 Day | May 5th | May 5th | Klein, Trinity; Abejide, Maria; Macedo, Joanna